# Phase-by-Phase Study Plan for LLM-Based Educational Question Generation & Evaluation

### Early January (Weeks 1–2): Rubric Validation & Refinement

| Phase | Focus | Milestones |
| --- | --- | --- |
| Phase 0 | Study scoping & infrastructure | - Storybook corpus finalized and cleaned - Human question datasets normalized - Repository structure and naming conventions finalized - Reproducibility README and experiment configuration template completed |
| Phase 1 (start) | Rubric drafting | - Literature-grounded rubric dimensions identified - Initial 1–5 scale rubric drafted |
| Phase 1 (end) | Rubric validation | - Educator review incorporated - Pilot rubric reliability study completed - Rubric v1.1 finalized and frozen |

Checkpoint: Experimental scaffolding completed + Final evaluation rubric locked

### Mid January (Weeks 3–4): Prompt Engineering & Pilot Testing

| Phase | Focus | Milestones |
| --- | --- | --- |
| Phase 2 | Prompt strategy | - Zero-shot and few-shot prompts designed - Pilot generation on small subset - Output format compliance and hallucination checks - Final prompts versioned and archived |

Checkpoint: Prompt strategy locked across all models

### Late January – Early February (Weeks 5–6): Large-Scale Generation

| Phase | Focus | Milestones |
| --- | --- | --- |
| Phase 3 | LLM question generation | - Full generation runs across all models × prompt types - Outputs validated and consolidated into llm_questions.csv |

Checkpoint: All LLM outputs finalized

### February (Weeks 7–9): Human Evaluation & Parallel Writing

| Phase | Focus | Milestones |
| --- | --- | --- |
| Phase 4 | Human evaluation | - Annotation interface deployed - Rater training completed - Human scoring finished |
| Phase 7 (start) | Writing | - Methods section drafted - Rubric and prompt methodology written |

Checkpoint: Human evaluation dataset complete

### Late February – Early March (Weeks 10–11): LLM-as-Judge & Automation

| Phase | Focus | Milestones |
| --- | --- | --- |
| Phase 5 | LLM-as-judge | - Judge prompts finalized - LLM scoring runs completed - Human–LLM alignment metrics computed |
| Phase 6 | Automated evaluation | - Feature extraction completed - ML/LLM evaluators trained and evaluated |

Checkpoint: All quantitative results available

### March (Weeks 12–13): Synthesis & Finalization

| Phase | Focus | Milestones |
| --- | --- | --- |
| Phase 7 (end) | Synthesis & reporting | - Cross-RQ synthesis completed - Results and Discussion finalized - Figures, tables, appendices completed - Full thesis draft submitted for advisor feedback |

## Phase 0: Study Scoping and Infrastructure Setup

Purpose: Ensure reproducibility, transparency, and clean experimental control before any generation or evaluation.

### 0.1 Dataset Finalization (Storybook Corpus)

Tasks

- Identify early reading story books (digital copies)

- Extract:

  - Page-by-page sentences

Deliverables

- Storybook_contexts.csv

### 0.2 Human Question Dataset Preparation

Tasks

- Collect human-authored questions from Dr. Yang’s team (Shay/Dr Yang will send)

- Normalize formatting:

  - Remove teacher notes

  - Standardize phrasing

- Annotate:

  - Intended grade

  - Intended learning objective (if available)

Deliverables

- human_questions_raw.csv

- human_questions_cleaned.csv

### 0.3 Experimental Infrastructure

This phase also establishes experimental controls that apply across all prompt-based generation runs, including consistent naming conventions for prompt types, versioned storage of all prompt templates, and run identifiers that allow prompt strategies (zero-shot vs. few-shot) to be traced and compared reproducibly. Detailed prompt design and testing are described in Phase 2.

Tasks

- Set up repository structure:

/data

/book content

/human_questions     (Shay/Dr Yang will send)

/llm_questions

/evaluations   (Shay/Dr Yang will send)

/prompts

ZeroShot

FewShot

/rubrics

/analysis

- Fix random seeds where applicable

- Define naming conventions for:

  - Model

  - Prompt type

  - Run ID

Deliverables

- Reproducibility README

- Experiment configuration template

## Phase 1: Rubric Design & Validation

### 1.1 Literature-Grounded Rubric Drafting

Tasks

- Survey literature on:

  - Question quality

  - Reading comprehension assessment

  - Dialogic reading

  - CROWD framework (adapted for early literacy)

- Extract rubric dimensions:

  - Grammaticality

  - Relevance

  - Answerability

  - Pedagogical usefulness

  - Cognitive demand

  - Age appropriateness

  - CROWD alignment

Deliverables

- Rubric dimension table with citations

- Initial rubric descriptors (1–5 scale)

### 1.2 Educator Consultation & Iteration

Tasks

- Review rubric with:

  - Dr. Yang

  - Dr. Chen

- Revise:

  - Language clarity

  - Scoring anchors

  - Redundancy between dimensions

Deliverables

- Final rubric v1.0

- Rubric annotation guidelines

### 1.3 Pilot Rubric Reliability Study

Tasks

- Select small sample (≈50 questions)

- Have ≥2 human raters score independently

- Compute:

  - Inter-rater reliability (Cohen’s κ / ICC)

  - Internal consistency (Cronbach’s α)

Deliverables

- Reliability analysis report

- Refined rubric v1.1

## Phase 2: LLM Configuration & Prompt Engineering

### 2.1 LLM Selection & Configuration

Models

- GPT-5.1

- Gemini Pro

Configuration Parameters

- Temperature: {0.2, 0.7}

- Max tokens: fixed across models

- System role: “Elementary literacy educator”

- Output constraints:

  - Question-only

  - One question per line

  - No explanations

Deliverables

- Model config table

- API parameter logs

### 2.2 Prompt Design

Prompt Types

- Zero-shot (generic)

- Few-shot (teacher exemplars)

Tasks

- Design parallel prompts across models

- Control for wording differences

- Store all prompts verbatim

Deliverables

- prompts_zero_shot.txt

- prompts_few_shot.txt

### 2.3 Prompt Pilot Testing

Tasks

- Generate questions on small subset

- Check:

  - Output consistency

  - Format compliance

  - Hallucinations

Deliverables

- Prompt refinement log

- Final prompt set (locked)

## Phase 3: Large-Scale Question Generation

### 3.1 Generation Runs

Tasks

- Run each context through:

  - GPT-5.1 × {zero, few}

  - Gemini Pro × same conditions

- Save outputs

Deliverables

- llm_questions.csv (book_title, author, llm_model, Prompt_type, crowd_label, question_generated)

## Phase 4: Human Evaluation of Questions

### 4.1 Human Evaluation Setup

Tasks

- Build annotation interface (Sheets / Qualtrics)

- Blind raters to:

  - Model

  - Human vs LLM origin

- Randomize order

Deliverables

- Human evaluation protocol

- Rater training document

### 4.2 Human Scoring

Tasks

- Score all questions using rubric

- Track time-on-task

- Collect qualitative comments

Deliverables

- human_eval_scores.csv

- human_eval_comments.csv

### 4.3 Human vs LLM Comparison

Tasks

- Aggregate scores by:

  - Model

  - Prompt type

  - Human vs LLM

- Statistical testing:

  - ANOVA / mixed-effects models

Deliverables

- Comparison tables

- Plots for thesis Results section

## Phase 5: LLM-as-a-Judge Evaluation

### 5.1 Judge Prompt Design

Tasks

- Convert rubric into evaluation prompt

- Enforce structured scoring output

- Test judge consistency

Deliverables

- LLM judge prompts

- Output schema

### 5.2 LLM Judging Runs

Tasks

- Have LLM score:

  - LLM-generated questions

  - Human-generated questions

- Repeat runs for stability

Deliverables

- llm_judge_scores.csv

### 5.3 Alignment Analysis

Tasks

- Compare LLM vs human scores:

  - Per dimension

  - Overall agreement

- Metrics:

  - Correlation

  - κ / ICC

Deliverables

- Alignment analysis report

- Dimension-wise reliability insights

## Phase 6: Automated Evaluation of Human Questions

### 6.1 Feature Extraction

Tasks

- Extract:

  - Length

  - Syntax features

  - Embeddings

- Label with human rubric scores

Deliverables

- Feature matrix

- Label set

### 6.2 ML & LLM-Based Models

Tasks

- Train lightweight regressors/classifiers

- Compare with LLM-only evaluation

Deliverables

- Model performance tables

- Feasibility assessment

## Phase 7: Synthesis, Interpretation, and Reporting

Tasks

- Identify:

  - Where LLMs excel

  - Where they fail

  - What humans do better

- Connect findings to pedagogy

### 7.2 Writing & Artifacts

Deliverables

- Thesis chapters:

  - Methods

  - Results

  - Discussion

- Public artifacts:

  - Rubric

  - Prompt templates

  - Evaluation protocol